Nordplus Adult 2016 (09/2016 - 08/2017) (NPAD-2016/10040)

Project

„Service design  know-how for rural SMEs strengthening the link between adult learning and working life in rural SME local food sector”.

1st partner meeting minutes

21.10.2016

Tamme Farm Herb Garden

- Partners agrees on deadlines for each task, are included in project PP last slide

- LC creat Google doc and send link to partners with all the PP, all Project docs etc.

- LC corrects the material content doc and send back to partners to translation and ellaboration the full material

- Partners should test the structure with steakholders – trainers, students, farmers etc.

- LC sends the flyer designed in EN for dissemination of the Handbook and project

- 2nd meeting in Norway in FEB or March, Jan sends the proposal for dates

- Partner put draft material text in Google doc before 2nd meeting, + links for  best exsamples in each chapter – so that each partner sees what is missing and how far each partner is. Exsamples are put seperatelly, when they are ready, buti n text – the weblinks.

- In 2nd partner meeting each partner prepeares PP for possible on-line solutions for Handbook. Olustvere will suggest the structure for on-line display.

- Each partneri s responsible for dissemination activities which are promissed in the application.