EC Leonardo da Vinci programme Project:

"Transfer of Quality Ensurance Tools for European Rural Tourism Sector"

Partner meeting, November 17, 2009

Brigg, North Lincolnshire (UK)
Venue to be confirmed, according to the Eurogites seminar “International Branding and

Marketing of Rural Tourism” (November 16, 2009)

Agenda

14:00		Project progress, overall situation.

~15:00		Interim report: financial issues, partner feedback and lessons learned.

~17:00		Next tasks and schedule:

-  Tool and its testing by partners

-  Rural tourism quality workshop

~ 18:30	Other issues, if relevant.

Things to do:

1. Translation of the Inspection manual – by Dec 4., 2009.

2. Project workshop on quality and partner meeting – May 12-13, 2009 (confirm the date of the partner meeting with all partners)

3.  Tool testing and comments by April 11, 2009 (to incorporate comments before the partner meeting in May)

4.  Presentation of the Tool at the Eurogites GA in 2009

5.  Send in more pictures for the tool (by April 11, 2009):

– leisure and outdoor activities

- pictures to illustrate cluster 4 – ambience, personal attention, hospitality

- pictures to illustrate safety - negative examples in all cases