Project

Transfer of Quality Ensurance Tools for European Rural Tourism Sector

QUALITOOL

Partner meeting minutes

Brigg, North Lincolnshire (UK)Nov 17, 2009

Participants:

Renata Kosi, Chamber of Agriculture and Forestry of Slovenia, Agriculture and Forestry Institute Celje

Klaus Ehrlich, EuroGites

Javier Cansinos Cabello, RAAR

Peggy Balitsari, Guest Inn Greek Network of Rural Accommodation

Kiril Kaloyanov, BAAT

Asnāte Ziemele, LLTA Lauku ceļotājs

Antra Damberga, LLTA Lauku ceļotājs

Asnāte Ziemele presented the financial report issues. The Interim report has been handed in to the LdV Agency.  Most partners have spent 70% of the first payment.  Partner 5 has not reached 70%. It was agreed that the second payment will be transferred to the partner after 70% of the first payment have been spent, documents have been provided justifying the spendings, and after Lauku ceļotājs has received the 2nd payment from the LdV Aency. Partners  are presented brief summary of the financial reporting requirements – types of proof for payments by budget lines.

Partners discuss teh project progress. WP2 has been completed and the result – the RT state of art review has been produced and disseminated. The next tasks are discussed: testing of the Tool and International RT workshop.

The first version of the Tool has been programmed and is presented to partners online: www.serv.celotajs.lv/eurogites . The partners agree to test it online and give their comments by Nov 30. In the meantime, Lauku celotajs will make changes as discussed at the partner meeting: Self-check: explanations of the criteria removed from the self-check screen and to be accessible as comments (by Nov 30).

Partners are presented and discuss the pictures that are collected for the training Tool as examples of compliance and incompliance with the standard criteria. More pictures need to be supplied as there are many criteria for which illustrations are missing. It was agreed that partners will continue to send pictures and use all opportunities to make new specific pictures during field visits to RT accommodations. Pictures are needed for: negative examples for  all clusters. Positive and negative answers for: Services, Personal attention, Security clusters.  No particular deadline was agreed at the meeting, but please look through your archives by the end of the year and send what is available now.  Please name the pictures using the numbering and criteria reference from the list of Eurogites criteria. Example: 1.12.equipment_size_common_areas_good.jpg

Tool testing has to be completed by April 11 to be on time for presentation at the International RT workshop on May 26 in Riga.